## Summary
OneFlowe Task Tracker Summary
Reporting period: 13 July 2026 to 21 July 2026
Overall Status | Task Count
Completed | 87
Ready for commit | 2
Total | 89
Category | Completed | Ready for commit | Total
Data Migration & Product Management | 11 | 0 | 11
Refund Improvements | 12 | 0 | 12
Order & Budget Management | 16 | 0 | 16
User & Access Management | 13 | 0 | 13
Security & Reliability | 17 | 0 | 17
Deployment & System Fixes | 8 | 1 | 9
Order Notifications | 10 | 0 | 10
User Interface | 0 | 1 | 1

## Task Tracker
OneFlowe Task Tracker
Reporting period: 13 July 2026 to 21 July 2026
Task ID | Date | Category | Task / Functionality | Status | Client Review | Client Comments
OF-001 | 2026-07-13 | Data Migration & Product Management | Migrated 594 eligible K-Electric historical orders and their related order items. | Completed
OF-002 | 2026-07-13 | Data Migration & Product Management | Added validation so only complete and accurate legacy orders are migrated. | Completed
OF-003 | 2026-07-13 | Data Migration & Product Management | Added exclusion reporting for legacy orders that could not be migrated. | Completed
OF-004 | 2026-07-13 | Data Migration & Product Management | Added migration backups, rollback support, and duplicate-import prevention. | Completed
OF-005 | 2026-07-13 | Data Migration & Product Management | Protected stock, budgets, invoice numbering, and notifications from unwanted migration side effects. | Completed
OF-006 | 2026-07-13 | Refund Improvements | Enabled refund requests for users whose product prices are hidden. | Completed
OF-007 | 2026-07-13 | Refund Improvements | Added quantity-based refund selection without exposing monetary values. | Completed
OF-008 | 2026-07-13 | Refund Improvements | Added requested, refunded, and remaining quantity tracking. | Completed
OF-009 | 2026-07-13 | Refund Improvements | Added price-safe refund history for restricted users. | Completed
OF-010 | 2026-07-13 | Refund Improvements | Fixed the Super Admin refund review workflow. | Completed
OF-011 | 2026-07-13 | Refund Improvements | Allowed Super Admins to approve the exact pending refund request being reviewed. | Completed
OF-012 | 2026-07-13 | Refund Improvements | Preserved the original refund reason during approval. | Completed
OF-013 | 2026-07-13 | Refund Improvements | Automatically closed other pending requests after a refund was approved. | Completed
OF-014 | 2026-07-13 | Refund Improvements | Prevented duplicate, overlapping, and excessive refunds. | Completed
OF-015 | 2026-07-13 | Refund Improvements | Added safeguards for older refunds with incomplete item details. | Completed
OF-016 | 2026-07-13 | Refund Improvements | Added clearer refund status and review information. | Completed
OF-017 | 2026-07-13 | Refund Improvements | Fixed organization filtering in the product performance report. | Completed
OF-018 | 2026-07-14 | Data Migration & Product Management | Standardized 144 imported K-Electric product codes. | Completed
OF-019 | 2026-07-14 | Data Migration & Product Management | Updated historical order items to use the standardized product codes. | Completed
OF-020 | 2026-07-14 | Data Migration & Product Management | Prevented duplicate product codes regardless of capitalization or spacing. | Completed
OF-021 | 2026-07-14 | Data Migration & Product Management | Corrected automatic generation of the next product code. | Completed
OF-022 | 2026-07-14 | Data Migration & Product Management | Removed an incorrect cross-organization product assignment. | Completed
OF-023 | 2026-07-14 | Data Migration & Product Management | Added validation and rollback support for product-code updates. | Completed
OF-024 | 2026-07-16 | Order & Budget Management | Strengthened product availability checks during checkout. | Completed
OF-025 | 2026-07-16 | Order & Budget Management | Ensured orders use the correct organization price. | Completed
OF-026 | 2026-07-16 | Order & Budget Management | Added quantity, stock, and budget validation before order placement. | Completed
OF-027 | 2026-07-16 | Order & Budget Management | Prevented duplicate orders caused by retries or repeated clicks. | Completed
OF-028 | 2026-07-16 | Order & Budget Management | Protected order processing from simultaneous conflicting actions. | Completed
OF-029 | 2026-07-16 | Order & Budget Management | Improved order approval and rejection workflows. | Completed
OF-030 | 2026-07-16 | Order & Budget Management | Improved order fulfilment and payment workflows. | Completed
OF-031 | 2026-07-16 | Order & Budget Management | Enforced the correct sequence for delivery status updates. | Completed
OF-032 | 2026-07-16 | Order & Budget Management | Improved automatic order fulfilment after delivery. | Completed
OF-033 | 2026-07-16 | Order & Budget Management | Ensured stock and budgets are restored correctly when orders are rejected or deleted. | Completed
OF-034 | 2026-07-16 | Order & Budget Management | Protected budget and product-allocation usage from becoming inconsistent. | Completed
OF-035 | 2026-07-16 | Order & Budget Management | Prevented active budget commitments from being accidentally reset. | Completed
OF-036 | 2026-07-16 | Order & Budget Management | Improved invoice-number generation to prevent duplicates. | Completed
OF-037 | 2026-07-16 | Order & Budget Management | Restricted order deletion to safe and eligible orders. | Completed
OF-038 | 2026-07-16 | Order & Budget Management | Strengthened organization settings and prevented duplicate settings. | Completed
OF-039 | 2026-07-16 | Order & Budget Management | Added safeguards against invalid prices, quantities, refunds, stock, and budget values. | Completed
OF-040 | 2026-07-16 | User & Access Management | Added safer role, organization, branch, group, and account access management. | Completed
OF-041 | 2026-07-16 | User & Access Management | Prevented users from changing their own access level. | Completed
OF-042 | 2026-07-16 | User & Access Management | Protected Super Admin accounts from unauthorized management. | Completed
OF-043 | 2026-07-16 | User & Access Management | Prevented users from assigning roles above their own authority. | Completed
OF-044 | 2026-07-16 | User & Access Management | Automatically ended active sessions after important access changes. | Completed
OF-045 | 2026-07-16 | User & Access Management | Added secure bulk user importing with validation and duplicate checking. | Completed
OF-046 | 2026-07-16 | User & Access Management | Added branch and role mapping during user imports. | Completed
OF-047 | 2026-07-16 | User & Access Management | Added temporary-password generation and mandatory password changes. | Completed
OF-048 | 2026-07-16 | User & Access Management | Added secure credential handoff for imported users. | Completed
OF-049 | 2026-07-16 | User & Access Management | Added a controlled Super Admin account-creation process. | Completed
OF-050 | 2026-07-16 | User & Access Management | Added a direct login button and login URL to new-user welcome emails. | Completed
OF-051 | 2026-07-16 | Security & Reliability | Added stronger protection against unauthorized field and status changes. | Completed
OF-052 | 2026-07-16 | Security & Reliability | Strengthened organization and branch data separation. | Completed
OF-053 | 2026-07-16 | Security & Reliability | Secured login redirects and removed unsafe page-rendering behavior. | Completed
OF-054 | 2026-07-16 | Security & Reliability | Added stronger browser and page security protections. | Completed
OF-055 | 2026-07-16 | Security & Reliability | Added same-site protection for account and business actions. | Completed
OF-056 | 2026-07-16 | Security & Reliability | Improved session-cookie security. | Completed
OF-057 | 2026-07-16 | Security & Reliability | Added stronger protection for login and one-time password actions. | Completed
OF-058 | 2026-07-16 | Security & Reliability | Added stronger protection for uploads, imports, and administrative actions. | Completed
OF-059 | 2026-07-16 | Security & Reliability | Added request-size and result-size limits to prevent system overload. | Completed
OF-060 | 2026-07-16 | Security & Reliability | Secured image uploads with file-type, size, dimension, and content validation. | Completed
OF-061 | 2026-07-16 | Security & Reliability | Secured spreadsheet and data imports with strict validation and all-or-nothing processing. | Completed
OF-062 | 2026-07-16 | Security & Reliability | Protected spreadsheet exports from unsafe formulas. | Completed
OF-063 | 2026-07-16 | Security & Reliability | Secured database export and backup operations. | Completed
OF-064 | 2026-07-16 | Security & Reliability | Improved error messages while preventing sensitive system information from being exposed. | Completed
OF-065 | 2026-07-16 | Security & Reliability | Added safer handling of passwords, emails, environment settings, and service credentials. | Completed
OF-066 | 2026-07-16 | Security & Reliability | Updated core application packages to safer supported versions. | Completed
OF-067 | 2026-07-16 | Security & Reliability | Prepared staged database permission hardening and rollback procedures. | Completed
OF-068 | 2026-07-18 | User & Access Management | Completed consolidated credential preparation for 23 UBL accounts. | Completed
OF-069 | 2026-07-18 | User & Access Management | Reconciled existing UBL user records with the approved onboarding information. | Completed
OF-070 | 2026-07-18 | Deployment & System Fixes | Repaired missing support for branch baseline budgets. | Completed
OF-071 | 2026-07-18 | Deployment & System Fixes | Repaired budget add-on functionality. | Completed
OF-072 | 2026-07-18 | Deployment & System Fixes | Repaired scheduled-report storage and processing support. | Completed
OF-073 | 2026-07-18 | Deployment & System Fixes | Fixed database setup and initial configuration reliability. | Completed
OF-074 | 2026-07-18 | Deployment & System Fixes | Fixed database failures being shown as incorrect permission errors. | Completed
OF-075 | 2026-07-20 | Deployment & System Fixes | Added reliable AWS Amplify deployment configuration. | Completed
OF-076 | 2026-07-20 | Deployment & System Fixes | Added secure server settings for the hosted application. | Completed
OF-077 | 2026-07-20 | Deployment & System Fixes | Added automatic validation for missing deployment settings. | Completed
OF-078 | 2026-07-21 | Order Notifications | Added in-app and email notifications when an order is created. | Completed
OF-079 | 2026-07-21 | Order Notifications | Added notifications to the order creator when an order is approved. | Completed
OF-080 | 2026-07-21 | Order Notifications | Added notifications to the order creator when an order is rejected. | Completed
OF-081 | 2026-07-21 | Order Notifications | Added Super Admin notifications when a Branch Admin approves an order. | Completed
OF-082 | 2026-07-21 | Order Notifications | Added automatic retrying for failed notification emails. | Completed
OF-083 | 2026-07-21 | Order Notifications | Prevented duplicate order notifications. | Completed
OF-084 | 2026-07-21 | Order Notifications | Ensured email failures do not interrupt order processing. | Completed
OF-085 | 2026-07-21 | Order Notifications | Restricted notifications to the correct organization, branch, role, and recipient. | Completed
OF-086 | 2026-07-21 | Order Notifications | Removed sensitive prices and approval information from notification emails. | Completed
OF-087 | 2026-07-21 | Order Notifications | Improved notification refresh and unread-status handling. | Completed
OF-088 | 2026-07-21 | Deployment & System Fixes | Ensured previously skipped business-protection updates can be applied correctly. | Ready for commit
OF-089 | 2026-07-21 | User Interface | Improved the order-shop layout so the cart no longer overlaps pagination controls. | Ready for commit
OF-090 | 2026-07-22 | User Interface | On order portal added functionality to copy or send fulfillment token. | Ready for commit
OF-091 | 2026-07-22 | User Interface | On order page added delivery date in table | Ready for commit
OF-093 | 2026-07-22 | User Interface | UI changes in invoice. | Ready for commit